Employment website

Software development plan

Version 1.0

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 16/10/2025 | 1.0 | Initial version of project plan draft | Trần Nhật Dương |
| 24/10/2025 | 1.1 | Final version of project plan | Trần Nhật Dương |

Table of Contents

1. Introduction	4

1.1 Purpose	4

1.2 Scope	4

1.3 Overview	4

2. Project Overview	4

2.1 Project Purpose, Scope, and Objectives	4

2.2 Assumptions and Constraints	5

2.3 Project Deliverables	5

3. Project Organization	5

3.1 Organizational Structure	5

3.2 Roles and Responsibilities	5

4. Management Process	6

4.1 Project Estimates	6

4.2 Project Plan	6

4.2.1 Phase Plan	6

4.2.2 Iteration Objectives	6

4.3 Project Monitoring and Control	7

4.3.1 Requirements Management	8

4.3.2 Reporting and Measurement	8

4.3.3 Risk Management	8

4.3.4 Configuration Management	8

Software Development Plan

- Introduction

The introduction of the Software Development Plan provides an overview of the entire document. It includes purpose, scope, definitions, acronyms, abbreviations, references, and overview of this Software Development Plan.

  - Purpose

The purpose of the Project Plan is to gather all information necessary to control the project. It describes the approach to the development of the software and is the top-level plan generated and used by managers to direct the development effort.

The following people use the Software Development Plan:

- The project manager uses it to plan the project schedule and resource needs, and to track progress against the schedule.

- Project team members use it to understand what they need to do, when they need to do it, and what other activities they are dependent upon.

  - Scope

This Software Development Plan describes the overall plan to be used by the CDH project. 
The plans outlined in this document are based upon the product requirements as defined in the Vision Document.

  - Overview

This Project Plan contains the following information:

Project Overview — provides a description of the project's purpose, scope, and objectives.  It also defines the deliverables that the project is expected to deliver.

Project Organization — describes the organizational structure of the project team.

- Project Overview

  - Project Purpose, Scope, and Objectives

The main purpose of this project is to develop an efficient and user-friendly Employment Website that simplifies and digitalizes the recruitment process. It aims to create a convenient platform where job seekers can easily find and apply for suitable jobs, and employers can post vacancies, review applications, and manage recruitment activities effectively.

The objectives of the project are:

- To design and implement a complete web application integrating frontend, backend, and database layers.

- To ensure secure and smooth user authentication for different roles (applicants, employers, and admins).

- To provide interactive and responsive interfaces for both desktop and mobile browsers.

- To implement core functionalities such as job searching, application tracking, employer management, and admin supervision.

- To gain hands-on experience in applying modern web development technologies and collaborative teamwork practices.

The expected deliverables include a fully functional Job Portal web application, a structured database for managing users and job data, and complete documentation with system design, testing results, and a final presentation demonstrating the system’s main features.

  - Assumptions and Constraints

Assumptions:

  - Some team members are not yet familiar with web development concepts but are willing to learn and improve during the project.

  - The required development tools, frameworks, and libraries are open-source or freely available.

  - Online learning resources and documentation are accessible throughout the project period.

Constraints:

  - The project must be completed within the semester’s timeline

  - There is no external budget for paid hosting or professional tools.

  - The team size is small, which may affect task distribution and development speed.

  - Project Deliverables

| Artifact | Target delivery dates |
| --- | --- |
| Vision document | 24/10/2025 |
| Project plan | 24/10/2025 |
| Use case model | 6/11/2025 |
| Use case specification | 6/11/2025 |
| Software architecture development | 20/11/2025 |
| Class diagram | 20/11/2025 |

- Project Organization

  - Organizational Structure

  - Roles and Responsibilities

| Person | Role |
| --- | --- |
| Trần Nhật Dương, Team Leader, Developer, Business Analyst | Responsible for overall project management, task distribution, server development and maintenance, as well as communication and feedback collection with TA. |
| Đào Duy Hảo, Developer, UI designer | Responsible for job one type of user UI design and developing the frontend pages of the website. |
| Nguyễn Huỳnh Trọng Đức, Developer, UI designer | Designs and develops the user interface (UI) of another user to ensure a user-friendly and visually appealing experience. |
| Nguyễn Đình Chuẩn, Test manager, Developer Văn Phú Hiệu, Developer | Assisting the project manager in recording each sprint, implementing the test plan for the website, developing the UI team in frontend and supporting team for writing meeting records in each sprint. Responsible for developing the user interface, integrating APIs to fetch data, and handling logic processing with the server. |

- Management Process

  - Project Plan

    - Phase Plan

The Job Portal project is divided into three main phases following the Rational Unified Process (RUP): Inception, Elaboration, and Construction. The development process is organized into six sprints, each corresponding to one Project Assignment (PA), ensuring steady progress and clear deliverables throughout the project.

  - Inception Phase (Sprint 1-2 / PA0-PA1): The team proposes the project idea, identifies target users, outlines main features, and develops a project plan that includes scope, timeline, and constraints. Furthermore, implement and outline basic UI design and web pages.

  - Elaboration Phase (Sprint 3-4-5 / PA2-PA4): This phase focuses on developing the main structure of the website while finalizing essential documentation such as the requirement specification, use case model and software architecture. The team finalizes requirements, designs core system components (frontend, backend, database), and builds a solid foundation for implementation.

  - Construction Phase (Sprint 5-6 / PA5-PA6): This phase involves implementation, testing, and final release. The team develops the full web application, performs testing to ensure performance and reliability, and completes the final release and prepares for the project defense with TA.

4.1.2	Schedule timeline

PA0 - Week 1 - 27/09/2025

Focus: Discuss and finalize the project topic, define target users and key features, and prepare the team contract and project proposal.

Goal: All members of project team get familiar with required programming language, complete project ideas with target users and key features

| Task | Member | Timeline |
| --- | --- | --- |
| Generate project ideas with target users, key features | All members of team | 29/9/2025 |
| Complete team contract, project proposal content | All members of team | 29/9/2025 |
| Get familiar with required programming language | All members of team | 29/9/2025 |
| Prepare for team contract, project proposal | Trần Nhật Dương | 29/9/2025 |

PA0 - Week 2 - 4/10/2025

Focus: Basic outline of code structure and UI design

Goal:

- Design and implement basic UI for login and register pages.

- Develop initial home pages for Employer and Candidate.

- Set up the database and API connection for basic data handling.

- Prepare project proposal and team contract documentation.

| Task | Member | Deadline |
| --- | --- | --- |
| Implement login page | Nguyễn Huỳnh Trọng Đức | 13/10/2025 |
| Implement register page | Văn Phú Hiệu | 13/10/2025 |
| Candidate home page design and develop | Đào Duy Hảo | 20/10/2025 |
| Employer home page design and develop | Nguyễn Đình Chuẩn | 20/10/2025 |
| Basic database design and API setup | Trần Nhật Dương | 20/10/2025 |
| Prepare for team contract, project proposal | Trần Nhật Dương | 11/10/2025 |

PA1 — Week 1 - 11/10/2025

Focus: Basic Employer/Candidate frontend, backend outline

Goal: Build basic frontend pages for Employer and Candidate, and outline backend structure with initial database design and API connection.

| Task | Member | Timeline |
| --- | --- | --- |
| Merge code between login page and register page, API connection to server | Nguyễn Huỳnh Trọng Đức, Văn Phú Hiệu | 20/10/2025 |
| Candidate home page design and develop | Đào Duy Hảo | 20/10/2025 |
| Employer home page design and develop | Nguyễn Đình Chuẩn | 20/10/2025 |
| Database design, API outline | Trần Nhật Dương | 20/10/2025 |
| Prepare documentation | All members of team | 25/10/2025 |

PA1 — Week 2 - 18/10/2025

Focus: Implement key job-related features for Employer and Candidate and integrate updated API with backend.

Goal:

- Develop core job portal features including job posting, job listing with pagination, and CV upload.

- Enable Employers to manage job posts and candidate CVs effectively.

- Update and refine API endpoints to ensure smooth frontend - backend communication.

- Prepare project documentation for review.

| Task | Member | Timeline |
| --- | --- | --- |
| Job posting form of employer UI | Nguyễn Đình Chuẩn | 27/10/2025 |
| CV management of employer | Nguyễn Huỳnh Trọng Đức | 27/10/2025 |
| Job listing with pagination | Đào Duy Hảo | 27/10/2025 |
| Job filtering + CV upload | Văn Phú Hiệu | 27/10/2025 |
| Update API endpoint | Trần Nhật Dương | 27/10/2025 |
| Prepare documentation | All members of team | 25/10/2025 |

PA2 - Week 1 - 25/10/2025

Focus: Finalize profile management and job post functions, and complete backend API integration.

Goal:

- Implement display and update features for both Employer and Candidate profiles.

- Develop and connect job post update functions with the backend API.

- Handle API processing for retrieving job lists and job details.

- Finalize API endpoints to ensure full communication between frontend and backend.

- Complete documentation for current system development progress.

| Task | Member | Timeline |
| --- | --- | --- |
| Employer profile (display, update) | Nguyễn Đình Chuẩn | 3/11/2025 |
| Candidate profile (display, update) | Đào Duy Hảo | 3/11/2025 |
| Job post update | Nguyễn Huỳnh Trọng Đức | 3/11/2025 |
| API processing for getting job list and job detail | Văn Phú Hiệu | 3/11/2025 |
| Complete API endpoint | Trần Nhật Dương | 3/11/2025 |
| Prepare documentation | All members of team | 8/11/2025 |

PA2 - Week 2 - 1/11/2025

Focus: Complete key features include: response to candidate, CV label of employers, tracking application status

Goal:

- Implement the response-to-candidate feature, allowing employers to mark applications as viewed, rejected, or accepted.

- Develop CV labeling for employers to organize and manage received CVs effectively.

- Build the application tracking system for candidates to monitor employer responses and job application progress.

- Add the job saving function to let candidates save preferred job postings.

- Integrate backend authorization and admin login to secure system access and ensure role-based authentication.

| Task | Member | Timeline |
| --- | --- | --- |
| Response to candidate (reject, viewed, …) | Nguyễn Huỳnh Trọng Đức | 10/11/2025 |
| CV labeling | Nguyễn Đình Chuẩn | 10/11/2025 |
| Tracking application, receive response from employer | Văn Phú Hiệu | 10/11/2025 |
| Job saving | Đào Duy Hảo | 10/11/2025 |
| Authorization for backend | Trần Nhật Dương | 10/11/2025 |
| Admin login | Trần Nhật Dương | 10/11/2025 |
| Prepare documentation | All members of team | 8/11/2025 |

PA3 - Week 1 - 8/11/2025

Focus: Enhancement of the system’s User Interface and User Experience (UI/UX).

Goal: To improve the platform’s usability, visual design

| Task | Member | Timline |
| --- | --- | --- |
| UI update | All members of team | 17/11/2025 |
| Admin login | Trần Nhật Dương | 17/11/2025 |
| Prepare documentation | All members of team | 21/11/2025 |

PA3 - Week 2 - 15/11/2025

Focus: Implement core backend and frontend functionalities to enhance system reliability, automation, and user experience for both employers and job seekers.

Goal:

- Develop and integrate the payment feature to allow employers to post jobs securely.

- Implement AI-based CV recommendation to improve matching efficiency for employers.

- Add a reset password function to enhance account security and user accessibility.

- Build the admin statistic module to track system usage and recruitment activities.

- Finalize and submit project documentation summarizing system design and current progress.

| Task | Member |  |
| --- | --- | --- |
| Payment for job posting | Nguyễn Đình Chuẩn | 24/11/2025 |
| AI CV recommendation for employers | Nguyễn Huỳnh Trọng Đức | 24/11/2025 |
| Reset password function | Văn Phú Hiệu, Đào Duy Hảo | 24/11/2025 |
| Admin statistic function | Trần Nhật Dương | 24/11/2025 |
| Prepare documentation | All members of team | 21/11/2025 |

PA4 - 22/11/2025

Focus: Initial release of Job portal

Goal: Bug process, UI updation

| Task | Member | Timeline |
| --- | --- | --- |
| Bug identification | Nguyễn Đình Chuẩn | 12/12/2025 |
| Bug fixing | All members of team | 12/12/2025 |
| UI/UX improvement | Đào Duy Hảo, Nguyễn Huỳnh Trọng Đức | 12/12/2025 |

PA5 - 15/12/2025

Focus: The second release of Job portal

Goal: To deliver the final, fully functional version of the Job Portal with complete features, improved performance, and enhanced user experience.

| Task | Member | Timeline |
| --- | --- | --- |
| Bug identification | Nguyễn Đình Chuẩn | 20/12/2025 |
| Bug fixing | All member of team | 20/12/2025 |
| UI/UX improvement | Đào Duy Hảo, Nguyễn Huỳnh Trọng Đức | 20/12/2025 |
| Prepare documentation | All members of team | 20/12/2025 |

  - Project Monitoring and Control

    - Requirements Management

The requirements for this system are captured in the Vision document. Requested changes to requirements are captured in Change Requests are approved as part of the Configuration Management process.

    - Reporting and Measurement

Updated cost and schedule estimates, and metrics summary reports, will be generated at the end of each iteration.

The Minimal Set of Metrics, as described in the RUP Guidelines: Metrics, will be gathered on a weekly basis.  These include:

Earned value for completed tasks. This is used to re-estimate the schedule and budget for the remainder of the project, and/or to identify need for scope changes.

Total defects open and closed – shown as a trend graph. This is used to help estimate the effort remaining to correct defects.

Acceptance test cases passing – shown as a trend graph. This is used to demonstrate progress to stakeholders.

In addition, overall costs will be monitored against the project budget.

    - Risk Management

Risks will be identified in the Inception Phase using the steps identified in the RUP for Small Projects activity “Identify and Assess Risks”. Project risk is evaluated at least once per iteration and documented in this table. The risks of the greatest magnitude are listed first in the table.

| Risk Ranking (High, Medium, Low) | Risk Description and Impact | Mitigation Strategy and/or Contingency Plan |
| --- | --- | --- |
| Low | Team members get sick | Delay the deadline of that member or distribute another member for support |
| Medium | Imbalance in work division among team members. | Ensure tasks are distributed evenly based on members |
| High | A team member may give up or withdraw from the project for personal or other reasons. | Maintain regular communication to identify potential issues early; ensure tasks are documented and shared; motivate and support team morale |
| High | Not consistency in coding convention | Defined common coding convention in the inception phase of project |
| Medium | Team members are not familiar with required language of project | Conduct short training sessions or self-learning plans before implementation |

    - Configuration Management

Appropriate tools will be selected which provide a database of Change Requests and a controlled versioned repository of project artifacts.

All source code, test scripts, and data files are included in baselines. Documentation related to the source code is also included in the baseline, such as design documentation. All customer deliverable artifacts are included in the final baseline of the iteration, including executables.